## Slide 1
Client Meeting Minutes
Supervisor Meeting Minutes
Team Meeting Minutes

## Slide 2
Current Iteration
4
11
4 Aug 2018
– 17 Aug 2018
Upcoming Meetings
Internal
Client
Supervisor
Upcoming Events
Acceptance
17 Aug 2018
Thriving Stones Project
This project aims to deliver two end products - a Web Application and Mobile Application. The Web Application would allow the centre to manage their curriculum calendar, generate Financial Report according to desired templates, document important financial transactions, track overdue payments and trigger reminders to be sent to parents and selectively retrieve or update student details. The Mobile Application provides Attendance Taking functionalities and reminders which serves a significant role in the calculation of tutor’s salaries and helps tutors to track the progress of individual students so that they could adjust the lesson plans to better benefit the students.
Road Ahead
Proposal Submission
20 June 2018
Acceptance
17 Aug 2018
Mid Term
4 Oct 2018 – 10 Oct 2018
Poster Submission
29 Oct 2018
Final Presentation
19 Nov 2018 – 27 Nov 2018
6 August 2018, Mon

## Slide 3
Our Project
We will be building an integrated Web Application which aims to support the operations management of the centre and the administrative duties that are to be carried out by the tutors on a daily basis, provide a platform for parents to monitor the performance of their children and to encourage the students to work harder through the implementation of a Reward System.
Schedule Management
Creation of Curriculum Calendar
Updating of Curriculum Calendar
Assignment of Tutors to Tuition Sessions
Viewing of Curriculum Calendar
Financial Report Management
Creation of Financial Reports
Updating of Financial Reports
Creation & Updating of Expenses
Exporting of Financial Reports as CSV
Viewing of full Financial Report
Student Management
Registration of new Students
Updating of Student Information
Removal of Students from Database
Payment Tracking
Tracking of Payments made
Tracking of overdue payments
Receipt Generation
Generation of Receipts in PDF Format
Generation of Pay Slips in PDF Format
Attendance Taking
Tracking of Students’ Attendance
Tracking of Tutors’ Attendance
Dashboard
Summary of Financial Report
Weekly Lesson Schedule
Upcoming Class Listing
Classes in need of Replacement Tutors
Reward
Allocation of reward points
Updating of reward points
Tracking of reward points
Grades Tracking
Adding of Grades
Updating of Grades
Viewing of Grades
Deleting of Grades

## Slide 4
CORE
Accounts Module
Profile Management
Login/Logout
Reset Password
Admin Module
Access Control
User Management
Tutor Management
Student Management Module
Sign Ups
Data Retrieval
Managing Student Details
Financial Module
Exporting of Financial Report
Updating of Financial Report
Writing of new Financial Report
Viewing of Full Reports
Calculations for expenses. revenue, tutor fees and profits
Schedule Module
Creation of Schedule
Updating of Schedule
Viewing of Schedule
Expenses Module
Creation of Expenses
Updating of Expenses
Deleting of Expenses
SECONDARY
Receipts Module
Pay Slip Generation
Invoice Generation
GOOD-TO-HAVE
Search Module
Search Students
Search Tutors
Search Reports (By Month, By Year)
Dashboard Module
Summary of Financial Report
List of Late Payments
List of Classes which needs Replacement
Class Listing (With Class Sizes, Timings)
Weekly Lesson Schedule
Project Motivation
The education sector is an industry in which the team could relate to as students. Upon discussion with the client, the team understands that operational tasks carried out could take up to several hours in total per day due to the Paper-Based System currently implemented. The team recognises that the time allocated to these tasks could be shortened significantly with the implementation of a system and hence gave rise to the idea of this project.
Student Management Module
Creation of Students
Reading of Students
Updating of Students
Deleting of Students
Grades Module
Grades Modification
Adding of Grades
Grades Viewing
Attendance Module
Creation of Tutor & Student Attendance
Reading of Tutor & Student Attendance
Updating of Tutor & Student Attendance
Rewards Module
Creation of reward points
Updating of reward points
Reading of reward points
Grades Tracking
Creating Grades
Updating Grades
Deleting Grades
Reading Grades

## Slide 5
COMING SOON

## Slide 6
Task Metric
Score (%)
Action
Understand the root cause and take action immediately
Consult supervisor on next course of action
TM < 50
Re-estimate tasks for future iterations
Consume buffer days
Analyse cause of delay and adjust schedule appropriately
50 < TM <= 90
Roughly on track and to proceed as planned
90 < TM <= 110
Gross over-estimated effort required
Re-estimate tasks for future iterations
Add number of days gained to buffer days
110 < TM <= 150
Understand the root cause and take action immediately
Consult supervisor on next course of action
150 < TM

## Slide 7
Bug Metrics
Score (%)
Description
Unimportant. Typo Error or Small User Interface Misalignments
Low Impact (1 Point)
The System runs. However, some non-critical functionalities are not working.
High Impact (5 Points)
Total Points = 1 x Number of Low Impact Bugs + 5 x Number of High Impact Bugs + 10 x Number of Critical Impact Bugs
The System is down or is unusable after a short period of time. Bugs need to be fixed to continue.
Critical Impact (10 Points)
Total Points
Action
Fix During Buffer Time Only
Points <= 5
Used the Planned Debugging Time
5 < Points < 10
Stop current development and resolve the bug immediately. Project Manager to reschedule the project.
Points >= 10
Total Points
Mitigation Plan
Used the planned debugging time in the iteration
Points < 10
Stop current development and resolve the bug immediately. Project Manager to reschedule the project.
Points >= 10

## Slide 8
S/N | Risk Statement | Consequences | Likelihood | Impact | Level | Mitigation Plan
1 | Miscommunication of project requirements between the team and the client. | Product might not match the client’s needs and time would be spent on reconstructing the product to fit the client’s expectations, resulting in possible delay of the project progress. | High | Medium | A | To conduct frequent user testing in order to ensure that the implemented functionalities matches that of what the client desires and to receive constant feedback from the client so that the changes that have to be made to the system would not snowball and instead fixed consistently in small amount.
2 | The team might not be used to the new development environment and languages implemented for the system. | More time would be taken to complete a functionality and could result in a delay in project progress. | High | Low | B | To decide on the architecture of the system before the project officially commences and to have the team familiarise themselves with the selected languages and platforms. In addition, we would have 2 members with one being more experienced to work on different parts of one functionality so that when faced with issues, the members could seek help from the more experienced member and this reduces time taken to complete the functionality.
3 | There might be low confidence in the new system as the client has been implementing the paper-based system ever since the start of operations and might not be able to garner the same faith in the new system. | The client might not be willing to implement the system after the completion of the product, resulting in resource wastages. | Medium | Medium | B | Conduct Parallel Testing in which the client would implement both the paper-based and new system together for a period of 3 months to ensure that the new system is able to fully replace the old system.

## Slide 9
Iter 8
Iter 9
Iter 10
Iter 11
4 Oct – 10 Oct
Mid Term Presentation
3 Oct – 17 Oct
18 Oct – 1 Nov
2 Nov – 16 Nov
17 Nov – 27 Nov
Payment Module
SMS Reminder before payment date
SMS Reminder for late payments
Attendace Module
Attendance Taking for Tutors
Attendance Taking for Students
Payment Module
Payment Tracking
Receipts Module
Payslips to Tutors (PDF)
Invoices to Parents (PDF)
Poster Preparation
Dashboard Module
Overview of Financial Report
Overdue Payments
Class Information
Final Preparation (Slides, Rehearsal)
Final Preparation
UI Enhancement
29 Oct
Poster Submission
19 Nov – 27 Nov
Final Presentation
Usability & User Testing
Actual
Usability & User Testing

## Slide 10
Iter 0
Iter 1
Iter 2
Iter 3
20 Jun
Proposal Submission
6 Jun – 20 Jun
Requirements Gathering
Technical Research (Libraries, Frameworks)
Logo Design
Roles Assignment
Proposal Preparation
21 Jun – 4 Jul
Design ER Diagram
Use Case Diagram
Draft Sequence Diagrams
Firebase Database Setup
UI Design
5 Jul – 19 Jul
Account Module
Login/Logout (Web, App)
Reset Password (Web, App)
Access Control
Creation of Users Entity
20 Jul – 3 Aug
Usability &
User Testing
Admin Module
Creation of Tutor Accounts
Updating of Tutor Accounts
Reading of Tutor Accounts
Deleting of Tutor Accounts
Creation of Tutor Entity
Student Mgmt Module
Creation of Students
Updating of Students
Reading of Students
Deleting of Students
Grades Module
Creation of Grades
Updating of Grades
Reading of Tutor Accounts
Creation of Grades Entity
Classes Module
Creation of Classes Entity
Schedule Module
Creation of Schedule
Updating of Schedule
Iter 4
Iter 5
Iter 6
Iter 7
17 Aug
Acceptance
4 Aug – 18 Aug
Acceptance Preparation (Slides, Rehearsal)
Schedule Module
Viewing of Schedule
Push Notifications for Upcoming Classes
19 Aug – 2 Sep
3 Sep – 17 Sep
18 Sep – 2 Oct
Financial Module
Updating of Reports
Financial Module
Calculations (Expenses, Profits, Revenue)
Exporting of Reports to CSV
Viewing of Report
Financial Module
Exporting of Reports (CSV)
Attendance Module
Push Notifications for Attendance Taking
Usability & User Testing
Supervisor Meeting
27 Jul
Financial Module
Writing of Reports using given format
Search Module
Searching of Tutors
Searching of Students
Searching of Reports

## Slide 11
Client
Adam
Users
Management
Tutors
Parents
Students