## Bug Metrics
BUG METRICS
Iteration | Number of Bugs | Number of Low Impact Bugs | Number of High Impact Bugs | Number of Critical Impact Bugs | Bug Metrics | Mitigation Plan Implemented
1 | 0 | 0 | 0 | 0 | 0 | NA
2 | 6 | 2 | 4 | 0 | 22 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
3 | 2 | 0 | 2 | 0 | 32 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
4
5
6
7
8
9
10
11
Total | 0 | 0 | 0 | 0
Points Calculation : 1 x num(low) + num(high) + 10 x num(critical)

## Bug Log
No. | Iteration | Git Commit ID | Function | Description | Bug Metric Cause | Date Found | By Who? | Date Solved | Time taken (h) | Severity | Impact Score | Points accumulated per iteration | Status | Action Taken
1 | 2 | e94ff6c1c40151d7251a2711aeb1074123a5ac87 | Login (App) | The user with the correct email address is unable to login to the app | The username was retrieved from the database and validated against the input email address instead | 17 Jul 2018 | Hui Xin | 18 Jul 2018 | 1 | High | 5 | 5 | Resolved | Retrieve the email field from the database instead for validation of email input
2 | 2 | e94ff6c1c40151d7251a2711aeb1074123a5ac87 | Login (App) | Error Message was not displayed incorrectly | The error message displayed does not reflect whether the error lies in the password or email | 17 Jul 2018 | Hui Xin | 18 Jul 2018 | 0.2 | Low | 1 | 6 | Resolved | Correct the error messages displayed to be more specific
3 | 2 | 21094817ecc3a115a2307add56ff0c9213551fdd | Create Tutor (Web) | Tutor created is not reflected in the database | Wrong method used to store objects in database (SetValueAsync instead of SetValue) | 17 Jul 2018 | Shawn | 17 Jul 2018 | 0.5 | High | 5 | 11 | Resolved | Changed to method used in TutorDAO.
4 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter studentID which exists in database, the admin still be able to overwrite the existing record in the database | There is no validation of duplicate student | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 0.2 | Low | 1 | 12 | Resolved | Retrieve Student from database using studentID, if Student not exists then create a student, else display error message
5 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter invalid student data input, the admin still be able to create new student in database | There is no validation for student data inputs (StudentID, Phone number, age, gender, reqAmt, etc) | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 1.5 | High | 5 | 17 | Resolved | Create all necessary validation methods with corresponding error messages
6 | 2 | 8a7136c020a39d26976638658563e64f16ac38b3 | Create Tutor (Web) | Tutor created is not reflected in the database (after adding in validation) | Errors in regex that caused validation error | 2018-07-19 | Shawn | 2018-07-19 | 1 | High | 5 | 22 | Resolved | Resolved regex error
7 | 3 | a1171e265566f2979ce323ba65d73b4ea24b24a2 | Reset Password | Unable to retrieve the correct user from the database | Error in the retrieval method for tutors | 2018-07-29 | Zang Yu | 2018-08-02 | 0.5 | High | 5 | 27 | Resolved | Corrected the retrieval method by modifying the query
8 | 3 | 9c4cb779547b8ac11f7995e826ac6f2e7cc3700e | Create Tutor (Web) | Unable to create tutor when you leave the age field empty | Parse Exception Error due to parsing an empty age field | 2018-07-27 | Shawn | 2018-07-27 | 0.5 | High | 5 | 32 | Resolved | Added condition checking for that the age field is not empty before parsing it into an integer
9 | 4 | 64f05bd6476708bd71d1628c0e9031d649f36b0e | Create Admin | Admin is able to be created even when the password field is left empty | No validation for password field | 2018-08-13 | Shawn | 2018-08-13 | 0.2 | Low | 1 | 33 | Resolved | Added in validation for password field
10 | 4 |  | Create Student | Double error messages for invalid fields |  | 2018-08-13 | Shawn |  |  | Low | 1 | 34
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50