## Task Metric
Task Metrics
Iteration | Updated On | Planned Tasks | Actual Tasks | Task Metric | Mitigation Plan Implemented
1 | 2018-03-07 | 17 | 14 | 0.82353 | Reestimated the number of tasks for the future iterations and deducted the number of days behind schedule from buffer days
2 | 19/7/2018 | 30 | 28 | 0.93333 | Estimates are fairly on track and we are fairly on track.
3 | 2018-03-08 | 27 | 26 | 0.96296 | Estimates are fairly on track and we are fairly on track.
4 | 17/8/2018 | 29 | 27 | 0.93103 | Estimates are fairly on track and we are fairly on track.
5 | 2018-01-09 | 23 | 21 | 0.91304 | Estimates are fairly on track and we are fairly on track. Due to our tight deadline, we added in additional tasks in the next iteration
Metric Calculation : Actual Tasks / Planned Tasks