## Iteration 2
S/N | Functionality | Description | Test Inputs | Test Procedure | Expected Results | Actual result | Pass/Fail | Pass/Fail after debugging
1 | Login | Varify that admin users are able to login with the designated admin accounts | Username: admin Pwd: adminadmin | Input username into username field and password into password field before clicking login | Successful Login
2 | Login | Verify that tutors are able to login with the designated accounts | Username: amytan Pwd: amytan86 | Input username into username field and password into password field before clicking login | Successful Login
3 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: admin Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
4 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: amytan Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
5 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: admin Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
6 | Login | Verify that upon successful login of the admin account, the user would be brought to the administrator view | Username: admin Pwd: adminadmin | Input username into username field and password into password field before clicking login | Admin Homepage to be shown
7 | Login | Verify that upon successful login of the tutor account, the user would be brought to the tutor view | Username: amytan Pwd: amytan86 | Input username into username field and password into password field before clicking login | Tutor Homepage to be shown
8 | Logout | Verfiy that once user logs out of the system, the user would not be able to access any of the pages | - | Click on the logout button and access other pages thereafter | Error Accessing Page message to be shown
9 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Schedule page and ensure that the user is only able to view the finalised schedule | Error Accessing Page message to be shown
10 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Manage Users page and ensure that the user is unable to gain access | Error Accessing Page message to be shown
11 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Financial Report Generation page and ensure that the user is unable to gain access | Error Accessing Page message to be shown
12 | Account Management | Verify that the user is able to reset his password if the new password fits the requirements | Old Pwd: amytan86 New Pwd: amytan97 | Input old password and then input new password, then click on Reset Password | Password Reset Success
13 | Account Management | Verify that the user is unable to reset his password if the new password does not fits the requirements | Old Pwd: amytan86 New Pwd: amytan | Input old password and then input new password, then click on Reset Password | Password Reset Failure
14 | Account Management | Verify that the user is unable to reset his password if the old password is incorrect | Old Pwd: amytan8 New Pwd: amytan97 | Input old password and then input new password, then click on Reset Password | Password Reset Failure
15 | Management of User Accounts | Verify that if the user is logged in as an admin user, the user would be able to create new accounts for access into system for tutors | Tutor Name: Amy Tan Academic Level: P6 Subject: Maths Class: G1 ID: amytan86 | Login as an admin user and navigate to the Tutor Account Creation Page. Input the details into the corresponding field and click Create Tutor | Tutor Creation Successful
16 | Management of User Accounts | Verify that the user would not be able to create tutor accounts if the mandatory fields are missing | Tutor Name: Amy Tan Academic Level: P6 Subject: Maths Class: G1 ID: | Login as an admin user and navigate to the Tutor Account Creation Page. Input the details into the corresponding field and click Create Tutor | Error Message prompting user to key in all mandatory fields would be displayed
17 | Management of User Accounts | Verify that if the user is logged in as an admin user, the user would be able to remove tutor accounts when the need arises | - | Login as an admin user and navigate to the List of Tutor Page. Input the details into the corresponding field and click Create Tutor Select the tutor Amy Tan and press Delete | The tutor should be removed from the database
18 | Student Creation | Verify that when all the neccessary information are filled in, the admin user would be able to successfully create the Student record in the database | Name: Jenny Kim ID: G1366407U Age: 14 Gender: F Phone: 91978630 Address: Bukit Panjang Ring Rd Academic Level: Sec3 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Student Creation Successful | Sign Up Successfully. | Pass | Pass
19 | Student Creation | Verify that when mandatory fields are empty, the admin user would not be able to successfully create the Student record in the database | Name: Jenny Kim ID: G1366407U Age: 14 Gender: Phone: 91978630 Address: Bukit Panjang Ring Rd Academic Level: Sec3 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Student Creation Failure to be displayed | Student Creation Successful | Fail | Pass
20 | Student Creation | Verify that when there is a duplicate of student, the admin user would not be able to overwrite the existing record in the database | Name: Jenny Kim ID: G1366407U Age: 15 Gender: Phone: 91978635 Address: Jelebu Rd Academic Level: Sec4 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message prompting that there was already a record of the specified student | Able to overwrite the record. | Fail | Pass
21 | Student Creation | Verify that if the Student ID entered does not satisfy the format requirements, the creation of new student would not be successful | ID: G112/ T1234567Z | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Student ID | Student Creation Successful | Fail | Pass
22 | Student Creation | Verify that if the Age entered does not satisfy the format requirements, the creation of new student would not be successful | Age: -3/100 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Age | Student Creation Successful | Fail | Pass
23 | Student Creation | Verify that if the phone number entered does not satisfy the requirements of 8 digits, the creation of new student would not be successful | Phone No. : 833399/ 833399RZ | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Age | Student Creation Successful | Fail | Pass
24 | Student Creation | Verify that if the most recent school results's subject selected redundant, the creation of new student would not be successful | Most Recent School Result: English, English, Maths/ Maths, Science, Maths | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message, redundant subjects selected | Student Creation Successful | Fail | Pass
25 | Delete Student (Web) | Verify that all the data related to student will be deleted from database | No inputs | Click Rubbish Bin Icon on selected student | Student Deleted successfully and display message "Deleted Student record successfully" | Student Deleted successfully and display message "Deleted Student record successfully" | Pass | Pass
26 | Login (App) | Varify that admin users are able to login with the designated admin accounts | Email: admin Pwd: adminadmin | Input username into email field and password into password field before clicking login | Successful Login | Successful Login | Pass | Pass
27 | Login (App) | Verify that tutors are able to login with the designated accounts | Email: jerald@steppingstones.com.sg Pwd: jerald86 | Input email into email field and password into password field before clicking login | Successful Login | Error Message Username does not exist | Fail | Pass
28 | Login (App) | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Email: admin Pwd: adminadmin! | Input email into email field and password into password field before clicking login | Login Error (Wrong Password) | Error Message Username does not exist | Fail | Pass
29 | Login (App) | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Email: jerald@steppingstones.com.sg Pwd: jerald | Input email into email field and password into password field before clicking login | Login Error (Invalid Email / Password) | Error Message Username does not exist | Fail | Pass
30 | Login (App) | Verify that upon successful login of the account, the user would be brought to the dashboard view | Email: jerald@steppingstones.com.sg Pwd: jerald86 | Input email into email field and password into password field before clicking login | Dashboard to be shown | Error Login (Username does not exist) | Fail | Pass
31 | Account Management (App) | Verify that the user is able to receive his password reset email if they entered the registered email address | Email: jerald@steppingstones.com.sg | Input email in the email field | Password Reset Success Alert | Password Reset Success Alert | Pass
32 | Account Management (App) | Verify that the user is unable to receive his reset password email if he did not enter the registered email address | Email: huixin@gmail.com | Input email in the email field | Invalid Email Alert | Invalid Email Alert | Pass
33 | Account Management (App) | Verify that the user is unable to receive his reset password email if he left the email field blank | Email: | Input email in the email field | Invalid Email Alert | Invalid Email Alert | Pass
34 | Create Tutor (Web) | Verify that the tutor is able to be created | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Input relevant fields | Successfully Created Tutor | Failed to create user | Fail | Pass
35 | Create Tutor (Web) | Check ID verification | Tutor ID: S12345D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed ID to different format | Failed to create tutor | Failed to create tutor | Pass
36 | Create Tutor (Web) | Check ID verification | Tutor ID: S12345671 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed ID to different format | Failed to create tutor | Failed to create tutor | Pass
37 | Create Tutor (Web) | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed no to less than 8digits | Failed to create tutor | Failed to create tutor | Pass
38 | Create Tutor (Web) | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345678 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed no to more than 8digits | Failed to create tutor | Failed to create tutor | Pass
39 | Create Tutor (Web) | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed email to not have @steppingstones.com.sg | Failed to create tutor | Failed to create tutor | Pass
40 | Create Tutor (Web) | Check password verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: wasd123 | Changed password to wasd123 | Failed to create tutor | Failed to create tutor | Pass
41 | Create Tutor (Web) | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstone.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed email to @steppingstone.com.sg | Failed to create tutor | Failed to create tutor | Pass
42 | Create Tutor (Web) | Check for empty fields | Tutor ID: Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left ID empty | Failed to create tutor | Failed to create tutor | Pass
43 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left name empty | Failed to create tutor | Failed to create tutor | Pass
44 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left no empty | Failed to create tutor | Failed to create tutor | Pass
45 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left email empty | Failed to create tutor | Failed to create tutor | Pass
46 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: Tutor Gender: Male Tutor password: Generated | Left age empty | Failed to create tutor | Failed to create tutor | Pass
47 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Tutor password: Generated | Left gender empty | Failed to create tutor | Failed to create tutor | Pass
48 | Create Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: | Left password empty | Failed to create tutor | Failed to create tutor | Pass
49 | Delete Tutor (Web) | Validating tutorID | TutorID : S1234567D | Input fields correctly | Deleted Tutor | Deleted Tutor | Pass
50 | Delete Tutor (Web) | Validating tutorID | TutorID : S1234567 | Changed format of ID | Failed to delete tutor | Failed to delete tutor | Pass
51 | Delete Tutor (Web) | Validating tutorID | TutorID : 123 | Changed format of ID | Failed to delete tutor | Failed to delete tutor | Pass
52 | Update Tutor (Web) | Verify that the tutor is able to be updated | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Input relevant fields | Successfully Updated Tutor | Successfully Updated Tutor | Pass
53 | Update Tutor (Web) | Check ID verification | Tutor ID: S1234567 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed ID to different format | Failed to update tutor | Failed to update tutor | Pass
54 | Update Tutor (Web) | Check ID verification | Tutor ID: S12345671 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed ID to different format | Failed to update tutor | Failed to update tutor | Pass
55 | Update Tutor (Web) | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed no to less than 8digits | Failed to update tutor | Failed to update tutor | Pass
56 | Update Tutor (Web) | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345678 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed no to more than 8digits | Failed to update tutor | Failed to update tutor | Pass
57 | Update Tutor (Web) | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn Tutor Age: 23 | Changed email to not have @steppingstones.com.sg | Failed to update tutor | Failed to update tutor | Pass
58 | Update Tutor (Web) | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstone.com.sg Tutor Age: 23 | Changed email to @steppingstone.com.sg | Failed to update tutor | Failed to update tutor | Pass
59 | Update Tutor (Web) | Check for empty fields | Tutor ID: Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left ID empty | Failed to update tutor | Failed to update tutor | Pass
60 | Update Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left name empty | Failed to update tutor | Failed to update tutor | Pass
61 | Update Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left no empty | Failed to update tutor | Failed to update tutor | Pass
62 | Update Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: Tutor Age: 23 | Left email empty | Failed to update tutor | Failed to update tutor | Pass
63 | Update Tutor (Web) | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: | Left age empty | Failed to update tutor | Failed to update tutor | Pass
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105

## Iteration 3
S/N | Functionality | Description | Test Inputs | Test Procedure | Expected Results | Actual result | Pass/Fail | Pass/Fail after debugging
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
2 | Login | Verify that tutors are able to login with the designated accounts | Username: amytan Pwd: amytan86 | Input username into username field and password into password field before clicking login | Successful Login
3 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: admin Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
4 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: amytan Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
5 | Login | Verify that users with the correct username but incorrect password are unable to login with the designated accounts | Username: admin Pwd: adminadmin! | Input username into username field and password into password field before clicking login | Login Error
6 | Login | Verify that upon successful login of the admin account, the user would be brought to the administrator view | Username: admin Pwd: adminadmin | Input username into username field and password into password field before clicking login | Admin Homepage to be shown
7 | Login | Verify that upon successful login of the tutor account, the user would be brought to the tutor view | Username: amytan Pwd: amytan86 | Input username into username field and password into password field before clicking login | Tutor Homepage to be shown
8 | Logout | Verfiy that once user logs out of the system, the user would not be able to access any of the pages | - | Click on the logout button and access other pages thereafter | Error Accessing Page message to be shown
9 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Schedule page and ensure that the user is only able to view the finalised schedule | Error Accessing Page message to be shown
10 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Manage Users page and ensure that the user is unable to gain access | Error Accessing Page message to be shown
11 | Account Management | Verify that should the user logins with a tutor account, the user would not be able to access functionalities such as Schedule (Creation & Update), Managing of accounts, Financial Report Generation | Username: amytan Pwd: amytan86 | Input username into username field and password into password field then click login. Click on the Financial Report Generation page and ensure that the user is unable to gain access | Error Accessing Page message to be shown
14 | Account Management | Verify that the user is unable to reset his password if the old password is incorrect | Old Pwd: amytan8 New Pwd: amytan97 | Input old password and then input new password, then click on Reset Password | Password Reset Failure
15 | Management of User Accounts | Verify that if the user is logged in as an admin user, the user would be able to create new accounts for access into system for tutors | Tutor Name: Amy Tan Academic Level: P6 Subject: Maths Class: G1 ID: amytan86 | Login as an admin user and navigate to the Tutor Account Creation Page. Input the details into the corresponding field and click Create Tutor | Tutor Creation Successful
16 | Management of User Accounts | Verify that the user would not be able to create tutor accounts if the mandatory fields are missing | Tutor Name: Amy Tan Academic Level: P6 Subject: Maths Class: G1 ID: | Login as an admin user and navigate to the Tutor Account Creation Page. Input the details into the corresponding field and click Create Tutor | Error Message prompting user to key in all mandatory fields would be displayed
17 | Management of User Accounts | Verify that if the user is logged in as an admin user, the user would be able to remove tutor accounts when the need arises | - | Login as an admin user and navigate to the List of Tutor Page. Input the details into the corresponding field and click Create Tutor Select the tutor Amy Tan and press Delete | The tutor should be removed from the database
18 | Student Creation | Verify that when all the neccessary information are filled in, the admin user would be able to successfully create the Student record in the database | Name: Jenny Kim ID: G1366407U Age: 14 Gender: F Phone: 91978630 Address: Bukit Panjang Ring Rd Academic Level: Sec3 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Student Creation Successful
19 | Student Creation | Verify that when mandatory fields are empty, the admin user would not be able to successfully create the Student record in the database | Name: Jenny Kim ID: G1366407U Age: 14 Gender: Phone: 91978630 Address: Bukit Panjang Ring Rd Academic Level: Sec3 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Student Creation Failure to be displayed
20 | Student Creation | Verify that when there is a duplicate of student, the admin user would not be able to overwrite the existing record in the database | Name: Jenny Kim ID: G1366407U Age: 15 Gender: Phone: 91978635 Address: Jelebu Rd Academic Level: Sec4 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message prompting that there was already a record of the specified student
21 | Student Creation | Verify that if the Student ID entered does not satisfy the format requirements, the creation of new student would not be successful | ID: G112/ T1234567Z | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Student ID
22 | Student Creation | Verify that if the Age entered does not satisfy the format requirements, the creation of new student would not be successful | Age: -3/100 | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Age
23 | Student Creation | Verify that if the phone number entered does not satisfy the requirements of 8 digits, the creation of new student would not be successful | Phone No. : 833399/ 833399RZ | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message regarding Age
24 | Student Creation | Verify that if the most recent school results's subject selected redundant, the creation of new student would not be successful | Most Recent School Result: English, English, Maths/ Maths, Science, Maths | Login as an admin user and navigate to the Sign Ups Page. Input the information as specified into the corresponding fields and click Sign Up | Error Message, redundant subjects selected
25 | Delete Student | Verify that all the data related to student will be deleted from database | No inputs | Click Rubbish Bin Icon on selected student | Student Deleted successfully and display message "Deleted Student record successfully"
26 | Create Tutor | Verify that the tutor is able to be created | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Input relevant fields | Successfully Created Tutor
27 | Create Tutor | Check ID verification | Tutor ID: S12345D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed ID to different format | Failed to create tutor
28 | Create Tutor | Check ID verification | Tutor ID: S12345671 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed ID to different format | Failed to create tutor
29 | Create Tutor | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed no to less than 8digits | Failed to create tutor
30 | Create Tutor | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345678 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed no to more than 8digits | Failed to create tutor
31 | Create Tutor | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed email to not have @steppingstones.com.sg | Failed to create tutor
32 | Create Tutor | Check password verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: wasd123 | Changed password to wasd123 | Failed to create tutor
33 | Create Tutor | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstone.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Changed email to @steppingstone.com.sg | Failed to create tutor
34 | Create Tutor | Check for empty fields | Tutor ID: Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left ID empty | Failed to create tutor
35 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left name empty | Failed to create tutor
36 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left no empty | Failed to create tutor
37 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: Tutor Age: 23 Tutor Gender: Male Tutor password: Generated | Left email empty | Failed to create tutor
38 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: Tutor Gender: Male Tutor password: Generated | Left age empty | Failed to create tutor
39 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Tutor password: Generated | Left gender empty | Failed to create tutor
40 | Create Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 Tutor Gender: Male Tutor password: | Left password empty | Failed to create tutor
41 | Delete Tutor | Validating tutorID | TutorID : S1234567D | Input fields correctly | Deleted Tutor
42 | Delete Tutor | Validating tutorID | TutorID : S1234567 | Changed format of ID | Failed to delete tutor
43 | Delete Tutor | Validating tutorID | TutorID : 123 | Changed format of ID | Failed to delete tutor
44 | Update Tutor | Verify that the tutor is able to be updated | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Input relevant fields | Successfully Updated Tutor
45 | Update Tutor | Check ID verification | Tutor ID: S1234567 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed ID to different format | Failed to update tutor
46 | Update Tutor | Check ID verification | Tutor ID: S12345671 Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed ID to different format | Failed to update tutor
47 | Update Tutor | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed no to less than 8digits | Failed to update tutor
48 | Update Tutor | Check number verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 912345678 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Changed no to more than 8digits | Failed to update tutor
49 | Update Tutor | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn Tutor Age: 23 | Changed email to not have @steppingstones.com.sg | Failed to update tutor
50 | Update Tutor | Check email verification | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstone.com.sg Tutor Age: 23 | Changed email to @steppingstone.com.sg | Failed to update tutor
51 | Update Tutor | Check for empty fields | Tutor ID: Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left ID empty | Failed to update tutor
52 | Update Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left name empty | Failed to update tutor
53 | Update Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: shawn@steppingstones.com.sg Tutor Age: 23 | Left no empty | Failed to update tutor
54 | Update Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: Tutor Email: Tutor Age: 23 | Left email empty | Failed to update tutor
55 | Update Tutor | Check for empty fields | Tutor ID: S1234567D Tutor Name: Shawn Tutor No: 91234567 Tutor Email: shawn@steppingstones.com.sg Tutor Age: | Left age empty | Failed to update tutor
56 | Create Tuition Grade | Check for empty fields | Select class: -LHRRS0ATm04Hiarglhj (English) Output lists of students in that class (Jimmy, Jenny) Select Examination: CA1 Select Subject: English Select Location: Center Grade: Empty | Left Grade empty | Failed to create grade
57 | Create Grade | Validating the field before create grade | Select class: -LHRRS0ATm04Hiarglhj (English) Select Examination: CA1 Select Subject: Chemistry Select Location: Center Grade: 88 | Input the information as specified into the corresponding fields and click Create Grade | Error Message Display "The grade created for this class can only be English"
58 | Create Grade | Validating the field before create grade | Select class: -LHRRS0ATm04Hiarglhj (English) Select Examination: CA1 Select Subject: English Select Location: Center Grade: 1000 | Input the information as specified into the corresponding fields and click Create Grade | Failed to create grade with errror message, pls enter valid grade
59 | Create Grade | Validating the field before create grade | Select class: -LHRRS0ATm04Hiarglhj (English) Select Examination: Select Examination Select Subject: Select Subject Select Location: Select Location Grade: 88 | Input the information as specified into the corresponding fields and click Create Grade | Failed to create grade with errror message, pls select location, subject, examination
60 | Create Grade | Validating duplicate data before create grade | Select class: -LHRRS0ATm04Hiarglhj (English) Select Examination: CA1 Select Subject: English Select Location: Center Grade: 88 | The CA1 grade for English is being created before however input the Examination field as CA1 | Failed to create grade with errror message, CA1 grade already exist
61 | Create Grade | Input all the neccessary information with correct data | Select class: -LHRRS0ATm04Hiarglhj (English) Select Examination: SA2 Select Subject: English Select Location: Center Grade: 88 | Input the information as specified into the corresponding fields and click Create Grade | Grade created successfully
62 | Retrieve Grade | Check for empty fields | StudentID: - | Doesn't input anything at StudentID field | Display message to input studentID
63 | Retrieve Grade | Input all the neccessary information with correct data | StudentID: G1234567L | Input the information as specified into the corresponding fields and click Retrieve | Display specific student's grades
64 | Update Grade | Check for empty fields | StudentID: - | Doesn't input anything at StudentID field | Display message to input studentID
65 | Update Grade | Input all the neccessary information with correct data | StudentID: G1234567L | Input the information as specified into the corresponding fields and click Update | Redirect to another page to add info
66 | Update Grade | Validating the data before update grade | Subject: Select Subject | The dropdown of subjets should only be the subjects that student is taking currently. For studentID G1234567L (Jimmy Lee) is enrolled in English and Add-Maths) | If the dropdown is not English and Add-Maths only then it is wrong else success
67 | Update Grade | Validating the field before update grade | Subject: Select Subject Level: Select Assessment Type Grade: - | Input the information as specified into the corresponding fields and click Update | Display all error messages. Pls select subject! Pls Select Assessment Type! Invalid Grade!
68 | Create Schedule | Check for empty fields | Subject: Select Subject Level: Select Level | Input the information as specified into the corresponding fields and click Save | Display all error messages. Pls select subject! Pls select level!
69 | Create Schedule | Input all the neccessary information with correct data | Subject: English Level: P3 Time: 8:30-10:00 20 Aug 1018 | Input the information as specified into the corresponding fields and click Save | Create schedule successfully
70 | Create Schedule | Able to save 2 classes with same date/time | Subject: English Level: P4 Time: 8:30-10:00 20 Aug 1018 | Input the information as specified into the corresponding fields and click Save | Create schedule successfully
71 | Update Schedule | Able to update schedule with all the correct input fields | Subject: English Level: P1 Day: Mon Start Time: 12 End Time: 2 Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Update schedule successfully | Schedule updated successfully | Pass
72 | Update Schedule | Unable to update schedule with unselected subject field | Subject: Level: P1 Day: Mon Start Time: 12 End Time: 2 Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Failure to update schedule with error message "Please select Subject" displayed | Error message "Please select subject displayed" | Pass
73 | Update Schedule | Unable to update schedule with unselected level field | Subject: English Level: Day: Mon Start Time: 12 End Time: 2 Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Failure to update schedule with error message "Please select Level" displayed | Error message "Please select level displayed" | Pass
74 | Update Schedule | Unable to update schedule with unselected day field | Subject: English Level: P1 Day: Start Time: 12 End Time: 2 Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Failure to update schedule with error message "Please select day" displayed | Error message "Please select day displayed" | Pass
75 | Update Schedule | Unable to update schedule with unselected start time field | Subject: English Level: P1 Day: Mon Start Time: End Time: 2 Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Failure to update schedule with error message "Please select start time" displayed | Error message "Please select start time displayed" | Pass
76 | Update Schedule | Unable to update schedule with unselected end time field | Subject: English Level: P1 Day: Mon Start Time: 12 End Time: Tutor Assigned: Irene | Select the corresponding fields into the form and click update schedule | Failure to update schedule with error message "Please select end time" displayed | Error message "Please select end time displayed" | Pass
77 | Reset Password | Users who provided the valid email would be able to receive a reset password email | Email: irene.ng.1997@steppingstones.com.sg | Enter the email into the email field | Email Sent Successfully | Error Message displayed | Fail | Pass
78 | Reset Password | Users who left the email empty would not be able to receive a reset password email | Email: | Enter the email into the email field | Error Message "Please enter a valid email" to be displayed | Error Message displayed | Pass
79 | Reset Password | Users who entered an invalid email would not be able to receive a reset password email | Email: irene.ng@steppingstones.com.sg | Enter the email into the email field | Error Message "Please enter a valid email" to be displayed | Error Message displayed | Pass
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97