## Bug Metrics
BUG METRICS
Iteration | Number of Bugs | Number of Low Impact Bugs | Number of High Impact Bugs | Number of Critical Impact Bugs | Bug Metrics | Mitigation Plan Implemented
1 | 0 | 0 | 0 | 0 | 0 | NA
2 | 6 | 2 | 4 | 0 | 22 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
3 | 2 | 0 | 2 | 0 | 32 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
4 | 5 | 5 | 0 | 0 | 37 | The bugs were fixed during the designated bug fixing sessions
5 | 2 | 1 | 0 | 1 | 48 | The bugs were discovered during the testing of the functionalities and hence we fixed it immediately upon discovery
6
7
8
9
10
11
Total | 0 | 0 | 0 | 0
Points Calculation : 1 x num(low) + num(high) + 10 x num(critical)

## Bug Log
No. | Iteration | Git Commit ID | Function | Description | Bug Metric Cause | Date Found | By Who? | Date Solved | Time taken (h) | Severity | Impact Score | Points accumulated per iteration | Status | Action Taken
1 | 2 | e94ff6c1c40151d7251a2711aeb1074123a5ac87 | Login (App) | The user with the correct email address is unable to login to the app | The username was retrieved from the database and validated against the input email address instead | 17 Jul 2018 | Hui Xin | 18 Jul 2018 | 1 | High | 5 | 5 | Resolved | Retrieve the email field from the database instead for validation of email input
2 | 2 | e94ff6c1c40151d7251a2711aeb1074123a5ac87 | Login (App) | Error Message was not displayed incorrectly | The error message displayed does not reflect whether the error lies in the password or email | 17 Jul 2018 | Hui Xin | 18 Jul 2018 | 0.2 | Low | 1 | 6 | Resolved | Correct the error messages displayed to be more specific
3 | 2 | 21094817ecc3a115a2307add56ff0c9213551fdd | Create Tutor (Web) | Tutor created is not reflected in the database | Wrong method used to store objects in database (SetValueAsync instead of SetValue) | 17 Jul 2018 | Shawn | 17 Jul 2018 | 0.5 | High | 5 | 11 | Resolved | Changed to method used in TutorDAO.
4 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter studentID which exists in database, the admin still be able to overwrite the existing record in the database | There is no validation of duplicate student | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 0.2 | Low | 1 | 12 | Resolved | Retrieve Student from database using studentID, if Student not exists then create a student, else display error message
5 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter invalid student data input, the admin still be able to create new student in database | There is no validation for student data inputs (StudentID, Phone number, age, gender, reqAmt, etc) | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 1.5 | High | 5 | 17 | Resolved | Create all necessary validation methods with corresponding error messages
6 | 2 | 8a7136c020a39d26976638658563e64f16ac38b3 | Create Tutor (Web) | Tutor created is not reflected in the database (after adding in validation) | Errors in regex that caused validation error | 2018-07-19 | Shawn | 2018-07-19 | 1 | High | 5 | 22 | Resolved | Resolved regex error
7 | 3 | a1171e265566f2979ce323ba65d73b4ea24b24a2 | Reset Password | Unable to retrieve the correct user from the database | Error in the retrieval method for tutors | 2018-07-29 | Zang Yu | 2018-08-02 | 0.5 | High | 5 | 27 | Resolved | Corrected the retrieval method by modifying the query
8 | 3 | 9c4cb779547b8ac11f7995e826ac6f2e7cc3700e | Create Tutor (Web) | Unable to create tutor when you leave the age field empty | Parse Exception Error due to parsing an empty age field | 2018-07-27 | Shawn | 2018-07-27 | 0.5 | High | 5 | 32 | Resolved | Added condition checking for that the age field is not empty before parsing it into an integer
9 | 4 | 64f05bd6476708bd71d1628c0e9031d649f36b0e | Create Admin | Admin is able to be created even when the password field is left empty | No validation for password field | 2018-08-13 | Shawn | 2018-08-13 | 0.2 | Low | 1 | 33 | Resolved | Added in validation for password field
10 | 4 | e47bb6334830165066737c5bc09795e511c447b4 | Create Student | Double error messages for invalid fields | Duplicated error message code | 2018-08-13 | Shawn | 16/08/2018 | 1 | Low | 1 | 34 | Resolved | Removed the second error messafe
11 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Wrong label for Assessment Type dropdown | Incorrect label for assessment type | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 35 | Resolved
12 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Missing error message when grade update is unsuccessful | The error message is not displayed when grade update is unsuccessful | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 36 | Resolved | Added error message in front end
13 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Missing error message when grade update is unsuccessful | Missing validation | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 37 | Resolved | Added error message in front end
14 | 5 |  | Attendance Taking | When attendance is marked, the checkbox doesn’t disappear and users are confused | Poor Interface Design | 31/08/2018 | Hui Xin | 31/08/2018 |  | Low | 1 | 38
15 | 5 | 669ddc1f9a6e3d8c79a4a2a85ba046489fe0d000 | Manage Acc | Crashes when accessing page | Did not change the method name when we renamed it in the DAO | 31/08/2019 | Hui Xin | 31/08/2018 | 0.1 | Critical | 10 | 48 | Resolved | Changed the method name accordingly
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50