## Slide 1
Client Meeting Minutes
Supervisor Meeting Minutes
Team Meeting Minutes

## Slide 2
Current Iteration
3
11
20 July 2018
– 3 Aug 2018
Upcoming Meetings
Internal
Client
Supervisor
Upcoming Events
Acceptance
17 Aug 2018
Thriving Stones Project
This project aims to deliver two end products - a Web Application and Mobile Application. The Web Application would allow the centre to manage their curriculum calendar, generate Financial Report according to desired templates, document important financial transactions, track overdue payments and trigger reminders to be sent to parents and selectively retrieve or update student details. The Mobile Application provides Attendance Taking functionalities and reminders which serves a significant role in the calculation of tutor’s salaries and helps tutors to track the progress of individual students so that they could adjust the lesson plans to better benefit the students.
Road Ahead
Proposal Submission
20 June 2018
Acceptance
17 Aug 2018
Mid Term
4 Oct 2018 – 10 Oct 2018
Poster Submission
29 Oct 2018
Final Presentation
19 Nov 2018 – 27 Nov 2018
27 July 2018, Fri

## Slide 3
Current Iteration
3
11
20 July 2018
– 3 Aug 2018
Upcoming Meetings
Internal
20 June 2018, Tuesday
Client
Supervisor
Upcoming Events
Acceptance
16 Aug 2018 – 21 Aug 2018
Thriving Stones Project
This project aims to deliver two end products - a Web Application and Mobile Application. The Web Application would allow the centre to manage their curriculum calendar, generate Financial Report according to desired templates, document important financial transactions, track overdue payments and trigger reminders to be sent to parents and selectively retrieve or update student details. The Mobile Application provides Attendance Taking functionalities and reminders which serves a significant role in the calculation of tutor’s salaries and helps tutors to track the progress of individual students so that they could adjust the lesson plans to better benefit the students.
Road Ahead
Proposal Submission
20 June 2018
Acceptance
16 Aug 2018 – 21 Aug 2018
Mid Term
4 Oct 2018 – 10 Oct 2018
Poster Submission
29 Oct 2018
Final Presentation
19 Nov 2018 – 27 Nov 2018
27 July 2018, Friday

## Slide 4
Our Project
We will be building an integrated system consisting of a Web Application and a Mobile Application. This system aims to support the operations management of the centre and the administrative duties that are to be carried out by the tutors on a daily basis.
Web Application
Schedule Management
  Creation of Curriculum Calendar
  Updating of Curriculum Calendar
  Assignment of Tutors to Tuition Sessions
  Viewing of Curriculum Calendar
Financial Report Management
  Creation of Financial Reports
  Updating of Financial Reports
  Creation & Updating of Expenses
  Exporting of Financial Reports as CSV
  Viewing of Full Financial Report
Student Management
  Registration of new Students
  Updating of Student Information
  Removal of Students from Database
Payment Tracking
  Tracking of Payments made
  Tracking of overdue payments
Receipt Generation
  Generation of Receipts in PDF Format
  Generation of Payslips in PDF Format
Mobile Application
Attendance Taking
  Tracking of Students’ Attendances
  Tracking of Tutors’ Attendances
  Push Notifications as reminders for Attendance Taking
Dashboard
  Summary of Financial Report
  Weekly Lesson Schedule
  Upcoming Class Listing (With Class Size and Timings)
  Classes in need of Replacement Tutors
Grades Tracking
  Adding of Grades to Students
  Updating of Students’ Grades
  Viewing of Students’ Grades
Project Motivation
The education sector is an industry in which the team could relate to as students. Upon discussion with the client, the team understands that operational tasks carried out could take up to several hours in total per day due to the Paper-Based System currently implemented. The team recognises that the time allocated to these tasks could be shortened significantly with the implementation of a system and hence gave rise to the idea of this project.

## Slide 5
CORE
Accounts Module
Profile Management
Login/Logout
Reset Password
Admin Module
Access Control
User Management
Tutor Management
Student Management Module
Sign Ups
Data Retrieval
Managing Student Details
Financial Module
Exporting of Financial Report
Updating of Financial Report
Writing of new Financial Report
Viewing of Full Reports
Calculations for expenses. revenue, tutor fees and profits
Schedule Module
Creation of Schedule
Updating of Schedule
Viewing of Schedule
Expenses Module
Creation of Expenses
Updating of Expenses
Deleting of Expenses
SECONDARY
Payment Module
Payment Tracking
SMS Reminders for Payment
SMS Reminders for Late Payment
List of Payments made
Updating of Payment Status
Classes Module
Upcoming Classes
Tutor Assignments
Push Notifications for upcoming classes
Student Management Module
Tutor Attendance Taking
Students Attendance Taking
Push Notifications (Reminder for Attendance Taking)
TERTIARY
Receipts Module
Pay Slip Generation
Invoice Generation
Grades Module
Grades Modification
Adding of Grades
Grades Viewing
GOOD-TO-HAVE
Search Module
Search Students
Search Tutors
Search Reports (By Month, By Year)
Dashboard Module
Summary of Financial Report
List of Late Payments
List of Classes which needs Replacement
Class Listing (With Class Sizes, Timings)
Weekly Lesson Schedule

## Slide 6
COMING SOON

## Slide 7
Task Metric
Score (%)
Action
Understand the root cause and take action immediately
Consult supervisor on next course of action
TM < 50
Re-estimate tasks for future iterations
Consume buffer days
Analyse cause of delay and adjust schedule appropriately
50 < TM <= 90
Roughly on track and to proceed as planned
90 < TM <= 110
Gross over-estimated effort required
Re-estimate tasks for future iterations
Add number of days gained to buffer days
110 < TM <= 150
Understand the root cause and take action immediately
Consult supervisor on next course of action
150 < TM

## Slide 8
Bug Metrics
Score (%)
Description
Unimportant. Typo Error or Small User Interface Misalignments
Low Impact (1 Point)
The System runs. However, some non-critical functionalities are not working.
High Impact (5 Points)
Total Points = 1 x Number of Low Impact Bugs + 5 x Number of High Impact Bugs + 10 x Number of Critical Impact Bugs
The System is down or is unusable after a short period of time. Bugs need to be fixed to continue.
Critical Impact (10 Points)
Total Points
Action
Fix During Buffer Time Only
Points <= 5
Used the Planned Debugging Time
5 < Points < 10
Stop current development and resolve the bug immediately. Project Manager to reschedule the project.
Points >= 10
Total Points
Mitigation Plan
Used the planned debugging time in the iteration
Points < 10
Stop current development and resolve the bug immediately. Project Manager to reschedule the project.
Points >= 10

## Slide 9
S/N | Risk Statement | Consequences | Likelihood | Impact | Level | Mitigation Plan
1 | Miscommunication of project requirements between the team and the client. | Product might not match the client’s needs and time would be spent on reconstructing the product to fit the client’s expectations, resulting in possible delay of the project progress. | High | Medium | A | To conduct frequent user testing in order to ensure that the implemented functionalities matches that of what the client desires and to receive constant feedback from the client so that the changes that have to be made to the system would not snowball and instead fixed consistently in small amount.
2 | The team might not be used to the new development environment and languages implemented for the system. | More time would be taken to complete a functionality and could result in a delay in project progress. | High | Low | B | To decide on the architecture of the system before the project officially commences and to have the team familiarise themselves with the selected languages and platforms. In addition, we would have 2 members with one being more experienced to work on different parts of one functionality so that when faced with issues, the members could seek help from the more experienced member and this reduces time taken to complete the functionality.
3 | There might be low confidence in the new system as the client has been implementing the paper-based system ever since the start of operations and might not be able to garner the same faith in the new system. | The client might not be willing to implement the system after the completion of the product, resulting in resource wastages. | Medium | Medium | B | Conduct Parallel Testing in which the client would implement both the paper-based and new system together for a period of 3 months to ensure that the new system is able to fully replace the old system.

## Slide 10
Iter 10
Iter 11
Iter 9
Iter 8
Iter 7
Iter 6
Iter 5
Iter 4
Iter 3
Iter 2
Iter 1
Iter 0
6 Jun
–
20 Jun
- Requirements Gathering
- Research Technical Knowledge and Libraries
- Logo Design
- Role Assignments
- Proposal Preparation
- Design ER Diagram
- Use Case Diagram
- Create Draft Sequence Diagrams
- Set up Firebase Database
- UI Design
Admin Module
- Login (Web & App)
- Reset Password (Web & App)
- Access Control
- User Management
Tutor Account Module
- Creation of Tutors
- Retrieve Tutors
- Update Tutors
- Delete Tutors
Student Management Module
- Sign Ups
- Retrieve Students
- Update Students
- Delete Students
Grade Module
- Creation of School Grades upon Sign Ups
- Update Registered Subjects Grade (Tuition)
- Viewing Grades
Classes Module
- Creation of Class Entity
Schedule Module
-Creation of Schedule
- Updating Schedule
4 Aug
–
18 Aug
- Acceptance
Preparation
Schedule Module
-View Schedule
- Updating Schedule
- Push Notification for Tutors before Classes using OneSignal
19 Aug
–
2 Sep
Financial Report Module
- Writing Reports using format given by sponsor
- Updating Financial Report
3 Sep
–
17 Sep
Search Module
Search Students
Search Tutors
Search Reports
Financial Report Module
- Calculation (Expense, Revenue, Profit)
- Exporting Reports (csv format)
- Viewing Report
18 Sep
–
2 Oct
Financial Report Module
- Exporting Reports (csv format)
Attendance Module
- Push Notification for Tutors to take attendance using OneSignal
- Mid Term Preparation
3 Oct
–
17 Oct
Payment Module
- SMS Reminder before payment date using Twiio
- SMS Reminder for Late Payment using Twiio
Attendance Module
- Taking Attendance for both Students and Tutors
18 Oct
–
1 Nov
- Poster Preparation
Payment Module
- Payment Tracking
Receipts Module
- Payslip for tutors (pdf)
- Invoice to parents after payment (pdf)
2 Nov
–
16 Nov
Dashboard Module
- Financial Report Summary
- Overdue Payment
- Class Information
- Final Preparation
17 Nov
–
27 Nov
- Final Preparation
- UI Enhancement
20 Jun
Proposal Submission
16 Aug – 21 Aug
Acceptance
4 Oct – 10 Oct
Mid Term Presentation
29 Oct
Poster Submission
19 Nov – 27 Nov
Final Presentation
Usability Testing
User Testing
Usability Testing
User Testing
Usability Testing
User Testing
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
Deployment
TestBuild using HockeyApp
21 Jun
–
4 Jul
5 Jul
–
19 Jul
20 Jul
–
3 Aug

## Slide 11
Iter 8
Iter 9
Iter 10
Iter 11
4 Oct – 10 Oct
Mid Term Presentation
3 Oct – 17 Oct
18 Oct – 1 Nov
2 Nov – 16 Nov
17 Nov – 27 Nov
Payment Module
SMS Reminder before payment date
SMS Reminder for late payments
Attendace Module
Attendance Taking for Tutors
Attendance Taking for Students
Payment Module
Payment Tracking
Receipts Module
Payslips to Tutors (PDF)
Invoices to Parents (PDF)
Poster Preparation
Dashboard Module
Overview of Financial Report
Overdue Payments
Class Information
Final Preparation (Slides, Rehearsal)
Final Preparation
UI Enhancement
29 Oct
Poster Submission
19 Nov – 27 Nov
Final Presentation
Usability & User Testing
Actual
Usability & User Testing

## Slide 12
Iter 0
Iter 1
Iter 2
Iter 3
20 Jun
Proposal Submission
6 Jun – 20 Jun
Requirements Gathering
Technical Research (Libraries, Frameworks)
Logo Design
Roles Assignment
Proposal Preparation
21 Jun – 4 Jul
Design ER Diagram
Use Case Diagram
Draft Sequence Diagrams
Firebase Database Setup
UI Design
5 Jul – 19 Jul
Account Module
Login/Logout (Web, App)
Reset Password (Web, App)
Access Control
Creation of Users Entity
20 Jul – 3 Aug
Usability &
User Testing
Admin Module
Creation of Tutor Accounts
Updating of Tutor Accounts
Reading of Tutor Accounts
Deleting of Tutor Accounts
Creation of Tutor Entity
Student Mgmt Module
Creation of Students
Updating of Students
Reading of Students
Deleting of Students
Grades Module
Creation of Grades
Updating of Grades
Reading of Tutor Accounts
Creation of Grades Entity
Classes Module
Creation of Classes Entity
Schedule Module
Creation of Schedule
Updating of Schedule
Iter 4
Iter 5
Iter 6
Iter 7
17 Aug
Acceptance
4 Aug – 18 Aug
Acceptance Preparation (Slides, Rehearsal)
Schedule Module
Viewing of Schedule
Push Notifications for Upcoming Classes
19 Aug – 2 Sep
3 Sep – 17 Sep
18 Sep – 2 Oct
Financial Module
Updating of Reports
Financial Module
Calculations (Expenses, Profits, Revenue)
Exporting of Reports to CSV
Viewing of Report
Financial Module
Exporting of Reports (CSV)
Attendance Module
Push Notifications for Attendance Taking
Usability & User Testing
Supervisor Meeting
27 Jul
Financial Module
Writing of Reports using given format
Search Module
Searching of Tutors
Searching of Students
Searching of Reports

## Slide 13
Client
Adam
Users
Management
Tutors