## Schedule Metrics
Task Metrics
Iteration | Updated On | Planned Tasks | Actual Tasks | Task Metric | Mitigation Plan Implemented
1 | 2018-03-07 | 17 | 14 | 0.82353 | Reestimated the number of tasks for the future iterations and deducted the number of days behind schedule from buffer days
2
3
4
5
Metric Calculation : Actual Tasks / Planned Tasks