## Bug Metrics
BUG METRICS
Iteration | Number of Bugs | Number of Low Impact Bugs | Number of High Impact Bugs | Number of Critical Impact Bugs | Bug Metrics | Mitigation Plan Implemented
1 | 0 | 0 | 0 | 0 | 0 | NA
2 | 6 | 2 | 4 | 0 | 22 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
3 | 2 | 0 | 2 | 0 | 32 | As the bugs were found during the testing sessions, we fixed it during the designated bug fixing sessions before proceeding on with the other tasks
4 | 5 | 5 | 0 | 0 | 37 | The bugs were fixed during the designated bug fixing sessions
5 | 6 | 4 | 0 | 1 | 52 | The bugs were discovered during the testing of the functionalities and hence we fixed it immediately upon discovery
6 | 7 | 5 | 2 | 0 | 66 | The bugs were discovered during the testing of the functionalities and hence we fixed it immediately upon discovery
7 | 10 | 3 | 5 | 3 | 124 | The bugs were discovered during the testing of the functionalities and hence we fixed it immediately upon discovery
8
9
10
11
Total | 17 | 8 | 7 | 3
Points Calculation : 1 x num(low) + num(high) + 10 x num(critical)

## Bug Log
No. | Iteration | Git Commit ID | Function | Description | Bug Metric Cause | Date Found | By Who? | Date Solved | Time taken (h) | Severity | Impact Score | Points accumulated per iteration | Status | Action Taken
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
2 | 2 | e94ff6c1c40151d7251a2711aeb1074123a5ac87 | Login (App) | Error Message was not displayed incorrectly | The error message displayed does not reflect whether the error lies in the password or email | 17 Jul 2018 | Hui Xin | 18 Jul 2018 | 0.2 | Low | 1 | 6 | Resolved | Correct the error messages displayed to be more specific
3 | 2 | 21094817ecc3a115a2307add56ff0c9213551fdd | Create Tutor (Web) | Tutor created is not reflected in the database | Wrong method used to store objects in database (SetValueAsync instead of SetValue) | 17 Jul 2018 | Shawn | 17 Jul 2018 | 0.5 | High | 5 | 11 | Resolved | Changed to method used in TutorDAO.
4 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter studentID which exists in database, the admin still be able to overwrite the existing record in the database | There is no validation of duplicate student | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 0.2 | Low | 1 | 12 | Resolved | Retrieve Student from database using studentID, if Student not exists then create a student, else display error message
5 | 2 | e226865b38512973bb3a9b5f5e5a3d36ca7f1730 | Sign Ups (Web) | When the admin enter invalid student data input, the admin still be able to create new student in database | There is no validation for student data inputs (StudentID, Phone number, age, gender, reqAmt, etc) | 18 Jul 2018 | Thet Thet Yee | 18 Jul 2018 | 1.5 | High | 5 | 17 | Resolved | Create all necessary validation methods with corresponding error messages
6 | 2 | 8a7136c020a39d26976638658563e64f16ac38b3 | Create Tutor (Web) | Tutor created is not reflected in the database (after adding in validation) | Errors in regex that caused validation error | 2018-07-19 | Shawn | 2018-07-19 | 1 | High | 5 | 22 | Resolved | Resolved regex error
7 | 3 | a1171e265566f2979ce323ba65d73b4ea24b24a2 | Reset Password | Unable to retrieve the correct user from the database | Error in the retrieval method for tutors | 2018-07-29 | Zang Yu | 2018-08-02 | 0.5 | High | 5 | 27 | Resolved | Corrected the retrieval method by modifying the query
8 | 3 | 9c4cb779547b8ac11f7995e826ac6f2e7cc3700e | Create Tutor (Web) | Unable to create tutor when you leave the age field empty | Parse Exception Error due to parsing an empty age field | 2018-07-27 | Shawn | 2018-07-27 | 0.5 | High | 5 | 32 | Resolved | Added condition checking for that the age field is not empty before parsing it into an integer
9 | 4 | 64f05bd6476708bd71d1628c0e9031d649f36b0e | Create Admin | Admin is able to be created even when the password field is left empty | No validation for password field | 2018-08-13 | Shawn | 2018-08-13 | 0.2 | Low | 1 | 33 | Resolved | Added in validation for password field
10 | 4 | e47bb6334830165066737c5bc09795e511c447b4 | Create Student | Double error messages for invalid fields | Duplicated error message code | 2018-08-13 | Shawn | 16/08/2018 | 1 | Low | 1 | 34 | Resolved | Removed the second error messafe
11 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Wrong label for Assessment Type dropdown | Incorrect label for assessment type | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 35 | Resolved
12 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Missing error message when grade update is unsuccessful | The error message is not displayed when grade update is unsuccessful | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 36 | Resolved | Added error message in front end
13 | 4 | 123d5e72a28deadf1651bc472a7a5fd03c954537 | Update Grade | Missing error message when grade update is unsuccessful | Missing validation | 16/08/2018 | Shawn | 19/08/2018 | 1 | Low | 1 | 37 | Resolved | Added error message in front end
14 | 5 |  | Attendance Taking | When attendance is marked, the checkbox doesn’t disappear and users are confused | Poor Interface Design | 31/08/2018 | Hui Xin | 31/08/2018 |  | Low | 1 | 38
15 | 5 | 669ddc1f9a6e3d8c79a4a2a85ba046489fe0d000 | Manage Acc | Crashes when accessing page | Did not change the method name when we renamed it in the DAO | 31/08/2018 | Hui Xin | 31/08/2018 | 0.1 | Critical | 10 | 48 | Resolved | Changed the method name accordingly
16 | 5 | 2efdaecb3eb4f2c981cb10fc39ad889836a46415 | Create Branch | Could not create branch record when you enter a phone number which starts with 6 | Wrong validation for the phone number field | 31/08/2018 | Hui Xin | 31/08/2018 | 0.1 | Low | 1 | 49 | Resolved | Edited the validation of the phone number to include numbers starting with 6
17 | 5 | 2efdaecb3eb4f2c981cb10fc39ad889836a46415 | Delete Tutor | Status Message displayed is "Failure! Something went wrong" when the delete was successful | Could not delete user successfully | 31/08/2018 | Hui Xin | 31/08/2018 | 0.1 | Low | 1 | 50 | Resolved | Column name for SQL was wrong for deleteUser method
18 | 5 | 2efdaecb3eb4f2c981cb10fc39ad889836a46415 | Delete Student | Status Message displayed is "Failure! Something went wrong" when the delete was successful | Could not delete user successfully | 31/08/2018 | Hui Xin | 31/08/2018 | 0.1 | Low | 1 | 51 | Resolved | Column name for SQL was wrong for deleteUser method
| 5 | 98f81d0849de43abd3076149e48edd5085463784 | Create Grade | The tutor should not be able to create a grade record for the student when the grade field is empty | Did not validate for empty field | 31/08/2018 | Hui Xin | 31/08/2018 | 0.1 | Low | 1 | 52 | Resolved | Add in validation for empty grade field
19 | 6 | 5dabbd9da7a806122e67bf08464958c3e8e3f850 | Reset Password | No error message displayed for failure of reset password | Input fields were not validated | 2018-10-09 | Hui Xin | 2018-10-09 | 2 | High | 5 | 56 | Resolved | Validate whether the user entered a valid username and email
20 | 6 | 71042bccd02bb44053d68b4e00527b7b9a5db9f6 | Update Subject Fees | Update status not displayed when you edit the same field the second time | The alert bar was not removed after every update atempt | 2018-10-09 | Hui Xin | 2018-10-09 | 0.1 | Low | 1 | 57 | Resolved | Remove and create a new alert bar on update alert display
21 | 6 | 45025fcf8af26a98297cdcf560234f0cc4af81d5 | Edit Subject | When removing one level from the subject during the Edit Subject functionality, the modal closes after removing one level | The page was set to reload after every delete | 2018-10-09 | Hui Xin |  |  | Low | 1 | 58 | Resolved | Implement ajax method instead to prevent the reloading of the page after removing of a single level
22 | 6 | 71042bccd02bb44053d68b4e00527b7b9a5db9f6 | Create Tutor | Email sent out is not properly displayed | Email is created with plaintext | 2018-10-09 | Hui Xin | 2018-10-09 | 0.5 | Low | 1 | 59 | Resolved | Edited the email to send with html template
23 | 6 | 814761bf1caf327fbf969ea3b1c8f9926c6744f9 | Create Schedule (Admin) | Upon deletion of class in filtered field, the page reloads to display all classes | The retrieval of data after delete is by branch | 2018-10-09 | Hui Xin | 2018-10-09 | 0.1 | Low | 1 | 60 | Resolved | Added in selectedLevelID to keep track of which filter has user activated
24 | 6 | 814761bf1caf327fbf969ea3b1c8f9926c6744f9 | Update Schedule (Admin) | Could not update the class information | Start date was not formatted properly and hence it could not be inserted into database | 2018-10-09 | Hui Xin | 2018-10-09 | 0.5 | High | 5 | 65 | Resolved | Formatted the dates before inserting into database
25 | 6 | e1f302ed5d06573e5a4f0d368698f9e0caa91aed | Create Student | The email is inserted into the school field and the school is inserted into the email field | Data was inserted wrongly into the database | 2018-10-09 | Hui Xin | 2018-10-09 | 0.5 | Low | 1 | 66 | Resolved | Switch the order of insertion for school and email columns
26 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Add Tutor Hourly Rate | The tutor hourly rate is not updated despite entering the correct format | There was no ajax call to update the tutor hourly rate in the database | 2018-09-29 | Hui Xin | 2018-09-29 | 1 | High | 5 | 71 | Resolved | Update the tutor hourly rate through the implementation of the ajax call
27 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Individual Class Registration | Crashes when registering for class and proceeding to Payment page | While deleting classes, the class_student_rel is not deleted from database and hence when the method is called, the classID would still appear but the class could not be retrieved from the database and hence that leads to the crash | 2018-09-29 | Hui Xin | 2018-09-29 | 0.5 | Critical | 10 | 81 | Resolved | Upon deleting a class, delete the class_student_rel records as well
28 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Tutor Schedule Viewing | The tutor could update the lesson date even when she has conflicting lessons | The method checking for overlapping lessons for tutors does not take into account corner cases such as other lessons under the same class and hence tends to return false which results in validation error | 2018-09-29 | Hui Xin | 2018-09-29 | 1 | High | 5 | 86 | Resolved | Checks for the classes and lessons instead of just lessons alone
29 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Header | Clicking the logo on the header crashes the system | The link of the logo was set incorrectly | 2018-09-29 | Hui Xin | 2018-09-29 | 0.1 | Low | 1 | 87 | Resolved | Link the logo to Dashboard.jsp
30 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Header | Could not activate account drop down when on TutorScheduling.jsp | The order for including footer.jsp and header.jsp was incorrect | 2018-09-29 | Hui Xin | 2018-09-29 | 0.1 | Low | 1 | 88 | Resolved | Include the header.jsp file before the footer.jsp file
31 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Create Student/Tutor/Admin | The student should be successfully created with all the required fields filled in correctly. However, upon clicking 'Create Student', there was an error message displayed and the student record could not be created | Database has an additional unnecessary column 'password' which was set to be not null and hence when inserted from front end the insert query could not be executed | 2018-09-29 | Hui Xin | 2018-09-29 | 1 | Critical | 10 | 98 | Resolved | Drop the password database
32 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Admin Scheduling (Create Class) | There was no validation on the format of start date, end date, start time and end time and hence when the user enters an invalid format, the system crashes | Include validation for date and time input fields before executing the inserting queries |  |  |  |  | Critical | 10 | 108
33 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Admin Scheduling (Update Class) | Upon successful update, there are 2 instances of lesson shown on the calendar (one is the before edit lesson and the other is the after edit lesson) | The old lessons are not deleted upon the insertion of the new lessons and hence there is a duplicated record in the database |  |  |  |  | High | 5 | 113
34 | 7 | 73c18bfd8226cd7c4c723bff1bccb7f812e34fc6 | Admin Scheduling (Update Lesson) | The user cannot update the lesson even when the fields are inputted correctly in the correct format | There was issue parsing the original datetime of the lesson and hence there is an error thrown even when the users entered the fields correctly |  |  |  |  | High | 5 | 118 |  | Substring the datetime retrieved from the database to ensure it would be able to be parsed for further calculations
35 | 7 | 1919c97994886c4ab6f135ebbd35814a1da3dcaf | Admin Scheduling (Create Class) | The reminder value inserted into the database was incorrect | Incorrect value used as parameter for the createClass method |  |  |  | 0.1 | Low | 1 | 119 |  | Replace the incorrect parameter with the correct parameter
36 | 7 | d3effd548dd2317629da54f9b52b7dcb2829998e | Access Control | When the user logins as a tutor, the user could access the admin functionalities if they enter the url manually in the address bar | The session attribute used to confirm the user's role was not set |  |  |  |  | High | 5 | 124 |  | Set the user's role in the session attribute
37 | 8 |  | Create Admin | User did not receive email when creating an admin account | [5 empty] | High | 5 | 129
38 | 8 |  | Delete Admin | Upon deleting admin account, the status message displays "Successfully deleted tutor" | [5 empty] | Low | 1 | 130
39 | 8 | 855a7f16b08c9c42efb4c0554ed107e716ab9910 | Delete Subject | Page keeps reloading after delete the levels that belong to subject | Auto Reload code after 5 seconds force the page to refresh | 26/09/2018 | MOH MOH | 26/09/2018 | 1 | Low | 1 | 131 | Resolved | Remove autoReload code and replaced with ajax
40 | 8 | a95c91c4c25e0fdc79044901293676739fc4c583 | Update subject fees | Subject fees are updated but for the class that comprised that fees never been updated | After added the new feature (subject fees linking to level), we forget to update the existing code | 2018-04-10 | MOH MOH | 2018-04-10 | 0.45 | High | 5 | 136 | Resolved | Update Query
41 | 8 | 45025fcf8af26a98297cdcf560234f0cc4af81d5 | Add Tutor Hourly Rate | Page keeps Refreshing For Creating hourly rate for tutor upon creation, update or deletion | Javascript added reload page function to see the latest change | 2018-04-10 | MOH MOH | 2018-04-10 | 0.45 | Low | 1 | 137 | Resolved | Change most of the code into AJAX so that the data will be updated even without reloading
42 | 8 | eeb83d15ddd220162a3019750946c3bcdf1c1002 | Remove Tutor | After tutor is deleted, all related info for that tutor is not removed | Many Related Data are added only after the tutor deletion functionality was implemented | 2018-05-10 | MOH MOH | 2018-05-10 | 5 | High | 5 | 142 | Resolved | Delete data from other tables which are related to the currently deleted tutor
43 | 8 | e7163a0808ef3811407a1a65c925ab68feb11b6a | Remove Subject | After subject is deleted, classes that offer that subject is not deleted | Added new features only after the subject deletion functionality was coded | 2018-05-10 | MOH MOH | 2018-05-10 | 5 | High | 5 | 147 | Resolved | Update class table with subject id = 0
44 | 8 |  | Remove Student
45 |  |  | Edit Lesson | For Tutor 's Class, no status of the edit action. And it won't display the currently replaced timetable to the assigned tutor
46 |  |  | Edit Class | Upon edit class, no error message being shown.Additionally , it will overwrite the previous tutor in the rest classes that the previous tutor is teaching
47 |  |  | Create Class | If currently class is in P1, it still allow the users to select any other level. (not bugs)
48
49
50